## Slide 1: Steering Committee Pack
ALEX Project 4th March 2021

## Slide 2: Agenda
1. Status Overview | 10 minutes
2. Capability Build – Milestone View | 15 minutes
3. Next Steps | 10 minutes
4. Lessons Learned | 10 minutes
5. AOB | 10 minutes

## Slide 3: Attendees / Introductions
Medtech | Geoff Sayer (CEO) Holly Hodgson (ALEX Product Owner) Gordon Inkson (Enterprise Architect) Mel Nepomunceno (Project Manager) Steve Cunnold (Software Delivery Manager) Mark Smith (CIO)
Umbrellar | Ross Robertson (Account Executive) Steve Hall (Service Delivery Manager) Rob Farnell (Senior Cloud Consultant)
Odin | Eric Van Der Sluis (Account Executive)
Microsoft | Darren Oxlee (Account Executive)
Aura | Laurence Ford (Account Executive)
Healthcare Interop Limited | David Hay (FHIR SME)
Patients First | Peter Jordan (FHIR SME)

## Slide 4: 1. Status Summary (focus on Build Project)
Key | Prior | Now | Comment
Medtech Stakeholders are committed |  |  | To date, our internal stakeholders are showing solid commitment to the project. Resources have been made available. No blockers.
Costs are Managed and On-Track |  |  | Build budget has overspent due to changes in FHIR scope causing re-work and time slippage. Current view is a circa $70k overspend against an approved baseline of $487k.
Benefits are Managed and On-Track |  |  | Amnesty revenue is being managed and currently meeting expectations. API revenue forecast is to meet NZ P&L expectations.
Schedule is Clear and On-Track |  |  | Delivery plan has extended by 3 weeks to complete UAT and Pen Testing.
Team is Mobilised and Performing |  |  | The build project team is meeting the demands of the project plan, whilst balancing other priorities.
Issues and Risks are Managed |  |  | Risks and Issues are being managed effectively. Remaining schedule risks are not material.
Delivery Partnerships are Performing |  |  | All delivery partners continue to meet the demands of the project plan.
Overall Status |  |  | Overall the build project has been a success. The team have delivered to promise in a challenging context.

## Slide 5: 2. Capability Build - Milestones
# | Key | Owner | Delivery Date | Status | Prior
1 | Commercials: Partner Contract | Holly | 5th March 2021 | All artefacts ready for legal review. Legal review underway (alongside PMS contract), which needs some tweaks. Moved date to mid Feb. With Geoff to resolve. | 
2 | Commercials: Full P&L | Holly / Mark | 27th November 2020 | Full P&L view in place. | 
3 | Process: Partner On Boarding | Holly | 23rd December 2020 | On boarding process complete. Off boarding will be designed and built post initial launch | 
4 | Process: Monthly Billing | Holly / Simeon | 29th January 2021 | Completed. | 
5 | Service Delivery: Third Party Contracts | Mark | 5th March 2021 | Umbrellar MSA signed. Odin LOE signed. Odin contract due this week. | 
6 | Service Delivery: CRM Workflow and Data | Mark / Isaac | 5th March 2021 | Detailed meetings held – late draft of document in place. Will complete this week | 
7 | Service Delivery: Staff Training | Mark / Isaac | 5th March 2021 | Plan to train service desk and operational staff this week. | 
8 | Service Delivery: Reports | Mark / Isaac | 20th March 2021 | Working with Umbrellar to define first set of performance reports. These are expected to be built in March | 

## Slide 6: 2. Capability Build - Milestones
# | Key | Owner | Delivery Date | Status | Prior
9 | Technology: Edge Solution | Gordon | 18th December 2020 | HCM solution defined. | 
10 | Technology: Edge Deployment | Gordon | 7th March 2021 | Edge Solution included in COVID release scheduled for 7th March | 
11 | Technology: Cloud Design | Gordon | 4th December 2020 | Odin chosen as middleware solution. Design phase can be considered closed, with the caveat that iterations in design will take place during build and operate phases. | 
12 | Technology: Sandbox | Gordon | 12th February 2021 | Sandbox is operational and Vendor onboarding in full swing. | 
13 | Technology: Cloud Deployment | Gordon | 12th March 2021 | UAT ongoing. ETA in 2 weeks. Pen Test ongoing. ETA in one week. PIA ongoing. ETA early next week. No issues. CSA ongoing. With Aura. ETA next week. | 
14 | Comms & Marketing: Marketing Release | Holly | 26th February 2021 | Initial comms complete – press release, webinar. | 
15 | Comms & Marketing: Engagement Approach | Holly | 12th March 2021 | Chrissie now allocated to make changes to Insight Portal – upload documentation. Video voice over updates on track for next week. | 
16 | Comms & Marketing: Product Roadmap (Initial Cut) | Holly | 31st January 2021 | Initial 24 month roadmap draft produced. Comms will set the expectation that the product roadmap will be customer-led and dynamic. | 

## Slide 7: 3. Next Steps (Apr-Jun)
ALEX NZ:
Mature the Service Delivery Model
  Formal refinement cycle, based on 3 x monthly checkpoints
  Service automation, based on Medtech CRM Project
Support Partner Service Launch
  Help our partners launch the first wave of ALEX-enabled services
  Bed-in our GP Consent Model
Enable Innovation
  Working in partnership with Microsoft and others, organise a set of ALEX-enabled hackathons to inspire market innovation
ALEX AU:
Design Business Model
  Scale the NZ model into AU and localise where appropriate
Build PMS Partnerships
  Secure the first wave of PMS partners
Iterate Operating Model / Initial Launch
  PoC to test assumptions
  Launch on Medtech AU PMS

## Slide 8: 4. Lessons Learned
Partnerships work. Our build partners and future Alex consumers have all worked collaboratively towards a shared goal within the bounds of transparency and trust. We need to respect and continue to live to these values.
FHIR Specifications need to be carefully crafted and thoroughly tested during Design phase. Downstream changes have proven expensive. We have been fortunate that the overspend associated with this issue was not larger, due to the commitment of the project team and partners.
Investing in a Proof of Concept and Formal Design phase was time and effort well spent. This greatly reduced the technical risks to the project and enabled partners to provide realistic build quotes and resource commitments.
Investing in smart tools and processes (Azure Dev Ops) helped mitigate contextual risks around resource availability and the quality of testing artefacts.
Open to the meeting – what else can we add?

## Slide 9: 5. AOB